## Audio Design Document
Sound | Trigger/Cue | Description | Who? | Recorded | Edited | Uploaded | File name
Soundtracks
Music (general) 1 | * | Main menu/talking to the lady of the house (stretch goal: she gets her own theme?) | Olivia | * | * | NEW 12/3 | music - kitchen.wav
Music (kitchen) | whenever player is in the kitchen and playing a level | Something a little faster paced or tense for the actual gameplay | Everyone
Music (menu) | * | * | Everyone
Kitchen ambience | whenever player is in the kitchen | Fire is probably constantly going, for one. what else should i include? | Brian | 2017-02-14 | 2017-02-15 | 2017-02-17 | Kitchen Ambience A
Characters
Moving | player(/underlings) move around in the kitchen | footsteps, not anything too crisp | Yao | * | * | 2017-02-16 | Sound Design_Chef_Female footsteps, Sound Design_Chef_Male footsteps
Eloise Awknowledge | player clicks on Eloise | info on characters: https://docs.google.com/spreadsheets/d/1wN3oGBl2Ny3oBF9t99p38jwPQMohXDNOKIT7_Un5_8k/edit#gid=0 | Olivia | 2017-02-23 |  | 2017-03-02 | Eloise Acknowledge
Amaud Awknowledge | player clicks on Amaud | info on characters: https://docs.google.com/spreadsheets/d/1wN3oGBl2Ny3oBF9t99p38jwPQMohXDNOKIT7_Un5_8k/edit#gid=0 | Brian | 2017-02-24 | 2017-02-24 | 2017-02-24 | Amaud Awknowledge
Guibert Awknowledge | player clicks on Guibert | info on characters: https://docs.google.com/spreadsheets/d/1wN3oGBl2Ny3oBF9t99p38jwPQMohXDNOKIT7_Un5_8k/edit#gid=0 | Jose
Aemilia Awknowledge | player clicks on Aemilia | info on characters: https://docs.google.com/spreadsheets/d/1wN3oGBl2Ny3oBF9t99p38jwPQMohXDNOKIT7_Un5_8k/edit#gid=0 | Yao
Lady of the Manor | Upon window | at the start of the level when the lady comes in to tell you something, a short gibberish awknowledgement | Olivia | 2017-02-23 |  | 2017-03-02 | Lady - not final
Chef Taste Tests | taste test | One for each level of satisfaction and disatisfaction. 3 levels for now, dissatisfaction, neutral, and satisfaction. androgynous - Vocal hum | Yao | 2017-02-23 | * | 2017-02-24
Consumer Dish Reaction | Dish served | * | Jose
Processes
Bake | * | * | Jose | * | * | 2017-02-17 | Oven
Roast | * | * | Jose | * | * | 2017-02-17 | Roasting
Pick up | Pick up | generic, same for all food, ambiguously soft/hard | Brian | 2017-02-23 | 2017-02-24 | 2017-02-24 | Pick Up
Put Down | Put Down | generic, same for all food, ambiguously soft/hard | Brian | 2017-02-23 | 2017-02-24 | 2017-02-24 | Put Down
Boiling | player boils water/thin soup | fast boil | Olivia | 2016-10-15 | 2016-10-22 | 2016-10-22 | fast boil loop.wav
* | * | goopier bubbling for a thick soup or stew | Olivia | * | 2016-10-29 | 2016-10-29 | slow boil loop.wav
Chopping | player cuts something | chopping, knife on wood will probably sound best (possible variations: chopping hard ingredients, chopping greens. should experiment with how different ingredients sound) | Olivia | 2016-10-15 | 2016-10-29 | 2016-10-29 | slow chop.wav or fast chop.wav. either is loopable if necessary
Mince | * | faster lighter chopping | Olivia | * | 2016-10-29 | 2016-10-29 | Use mince 1.wav for a standalone effect, or mince 2.wav for a looped effect
Sliver | * | more of a slicing? maybe just use mince effect for now | Olivia | 2017-02-17 | 2017-02-17 | 2017-02-17 | slice 1.wav and slice 2.wav
Grind (Pound/Press?) | player uses mortar and pestle | a satisfying scraping and grinding sound (like if it's all high end i think it won't sound good it needs to be alittle more solid than that probably) | Yao | * | * | 2017-02-16 | Sound Design_Chef_Grind_more wet_v2, Sound Design_Chef_Grind_v1, Sound Design_Chef_Pounding
Fry | player fries ingredient | hissing and popping oil | Olivia | 2016-10-15 | 2016-10-29 | 2016-10-29 | Frying (one shot).wav and Frying (loop).wav. "Frying (one shot)" is standalone and "Frying (loop)" is a loop. we can use them in conjunction (play 1, then loop 2) to make the effect last a long time
Add ingredients | player adds ingredient to wet dish | a small splash | Olivia | 2016-10-15 | 2016-11-12 | 2016-11-12 | add to wet 1.wav or add to wet 2.wav (i think i prefer #2, but #1 might be better for adding wet ingredients to wet ingredients?)'
* | player adds ingredient to dry dish | ? not sure might vary will come back to this | Olivia | * | 2016-11-12 | 2016-11-12 | add to dry.wav
Add seasoning | player adds spice | either a pepper shaker kind of noise/fine powder briefly scraped or scattered? | Olivia | 2016-10-15 | 2016-10-22 | 2016-10-22 | seasoning 3.wav
Misc UI
GUI Click | Click in Menu or Misc. | Click in Menu or Misc. | Yao | * | * | 2017-02-16 | Sound Design_Chef_GUI_v1, Sound Design_Chef_GUI_v2, Sound Design_Chef_GUI_v3, Sound Design_Chef_GUI_v4
Serve it Forth! | complete dish is delivered | positive sound! possibly a small bell ring | Olivia | 2017-02-17 | 2017-02-17 | 2017-02-17 | Dish Delivered.wav
Success! | Dinner has been completed, all dishes delivered. would presumably play after the last serve it forth effect | possibly a small musical snippet (do we want a separate effect for if the dinner was not well received?) | Olivia |  |  | 2017-03-31 | end of level concept 1 or end of level concept 2
Clock out of time | timer runs out | deeper, less cheery bell than the "serve it forth sound" | Brian | 2017-02-22 | 2017-02-24 | 2017-02-24 | Clock Out of Time.mp3
Grab Spinach from Pantry | * | * | Yao
Grab Eggs from Pantry | * | * | Yao
Grab Water from Pantry | * | * | Jose
Grab Chicken from Pantry | * | * | Jose
Grab Flour from Pantry | * | * | Olivia | 2017-02-23 | 2017-02-24 | 2017-02-24 | get flour.mp3
Grab Mustard from Pantry | * | * | Olivia | 2017-02-23 | 2017-02-24 | 2017-02-24 | get mustard seeds.mp3